## V3
DRIVE AND COOK - REORGANIZATION OF THE INFORMATION SYSTEM
March - July 2020
Project management
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
Logo creation | Project Manager | 1 | 550 | 550
Corporate identity | Project Manager | 1 | 550 | 550
Website maquette | Frontend developer | 1 | 300 | 300
Functional specification | Project Manager | 2 | 550 | 1100
User guide | Project Manager | 3 | 550 | 1650
Security audit | Network engineer | 7 | 550 | 3850
TOTAL PROJECT MANAGEMENT |  |  |  | 8000
Management of franchised services
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
QR Code data gestion | Software developer | 6 | 500 | 3000
Web application - Front office | FullStack developer | 8 | 450 | 3600
Web application - Back office | FullStack developer | 4 | 450 | 1800
Interface design | Frontend developer | 2 | 300 | 600
WebGL application | Frontend developer | 8 | 300 | 2400
Web server configuration | Network engineer | 2 | 550 | 1100
Bi-monthly reunion | Project Manager | 2 | 550 | 1100
TOTAL FRANCHISED SERVICES |  |  |  | 13600
Management of clients services
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
Online orders | Backend developer | 12 | 400 | 4800
Loyalty card gestion | Backend developer | 6 | 400 | 2400
Event planning | FullStack developer | 5 | 450 | 2250
Newsletter | Frontend developer | 4 | 300 | 1200
Multilingual interface | Frontend developer | 4 | 300 | 1200
Interface design | Frontend developer | 5 | 300 | 1500
Bi-monthly reunion | Project Manager | 2 | 550 | 1100
TOTAL CLIENTS SERVICES |  |  |  | 14450
TOTAL DEVELOPMENT |  |  |  | 28050
Network architecture and security
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
ESX hosting | Network engineer | 3 | 550 | 1650
Secure VPN connection | Network engineer | 6 | 550 | 3300
Warehouse internet access | Network engineer | 2 | 550 | 1100
Bi-monthly reunion | Project Manager | 2 | 550 | 1100
TOTAL NETWORK ARCHITECTURE AND SECURITY |  |  |  | 7150
TOTAL DEVELOPMENT AND ARCHITECTURE |  |  |  | 35200
TECH FEES
TASKS | PLAYER |  | UNIT COST | COST
ESX License |  | 1 | 3500 | 3500
Dedicated ESX Server |  | 6 | 600 | 3600
Domain name |  | 1 | 10 | 10
JetBrains licenses |  | 18 | 65 | 1170
TOTAL NETWORK ARCHITECTURE AND SECURITY |  |  |  | 8280
HANDLING FLAT FEE (15%) | all expenses made on behalf of the client
All tech costs are subject to changes related to providers, French taxes on IP and volumes
TOTAL |  |  |  | 51480
PLAYER |  | PERSON-DAY
Project Manager |  | 300
Frontend developer |  | 400
Backend developer |  | 450
FullStack developer |  | 500
Software developer |  | 550
Network engineer

## Feuil2
DRIVE AND COOK - REORGANIZATION OF THE INFORMATION SYSTEM
March - July 2020
Project management
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
Logo creation | Project Manager | 1 | 550 | 550
Corporate identity | Project Manager | 1 | 550 | 550
Website mock-up | Frontend developer | 1 | 300 | 300
Functional specification | Project Manager | 2 | 550 | 1100
User guides | Project Manager | 3 | 550 | 1650
Security audit | Network engineer | 7 | 550 | 3850
TOTAL PROJECT MANAGEMENT |  |  |  | 8000
Management of franchised services
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
QR Code data gestion | Software developer | 6 | 500 | 3000
Web application - Front office | FullStack developer | 8 | 450 | 3600
Web application - Back office | FullStack developer | 4 | 450 | 1800
Interface design | Frontend developer | 2 | 300 | 600
WebGL application | Frontend developer | 8 | 300 | 2400
Web server configuration | Network engineer | 2 | 550 | 1100
Bi-monthly reunion | Project Manager | 2 | 550 | 1100
TOTAL FRANCHISED SERVICES |  |  |  | 13600
Management of clients services
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
Online orders | Backend developer | 12 | 400 | 4800
Loyalty card gestion | Backend developer | 6 | 400 | 2400
Event planning | FullStack developer | 5 | 450 | 2250
Newsletter | Frontend developer | 4 | 300 | 1200
Multilingual interface | Frontend developer | 4 | 300 | 1200
Interface design | Frontend developer | 5 | 300 | 1500
Bi-monthly reunion | Project Manager | 2 | 550 | 1100
TOTAL CLIENTS SERVICES |  |  |  | 14450
TOTAL DEVELOPMENT |  |  |  | 28050
Network architecture and security
TASKS | PLAYER | PERSON-DAY | UNIT COST | COST
ESX hosting | Network engineer | 3 | 550 | 1650
Secure VPN connection | Network engineer | 6 | 550 | 3300
Warehouse internet access | Network engineer | 2 | 550 | 1100
Bi-monthly reunion | Project Manager | 2 | 550 | 1100
TOTAL NETWORK ARCHITECTURE AND SECURITY |  |  |  | 7150
TOTAL DEVELOPMENT AND ARCHITECTURE |  |  |  | 35200
TECH FEES
TASKS | PLAYER |  | UNIT COST | COST
ESX License |  | 1 | 3500 | 3500
Dedicated ESX Server |  | 6 | 600 | 3600
Domain name |  | 1 | 10 | 10
JetBrains licenses |  | 18 | 65 | 1170
TOTAL NETWORK ARCHITECTURE AND SECURITY |  |  |  | 8280
HANDLING FLAT FEE (15%) | all expenses made on behalf of the client
All tech costs are subject to changes related to providers, French taxes on IP and volumes
TOTAL |  |  |  | 51480
PLAYER |  | PERSON-DAY
Project Manager |  | 300
Frontend developer |  | 400
Backend developer |  | 450
FullStack developer |  | 500
Software developer |  | 550
Network engineer